## CpythonFuzz
Task ID | Subtasks | Description | Start date | End date | Status | Memo
1. Technique investigation and basic design | 1.1 | compiler testing survery, VM testing survey and technique design | 10/15/2022 | 10/30/2022 | 80% | may change during implementation
1. Two-Level Fuzzing framework | 1.1 | CPython instrumentation (Atheris for python and libfuzzer for C) | 2022-01-11 | 2022-10-11 | 100%
| 1.2 | Level-1 fuzzing: generate diverse python applications | 11/20/2022 | 11/28/2022 | 60% | framework done, wait for app generation part and debugging
| 1.3 | Level-2 fuzzing: for each application, generate diverse inputs with limited time budget | 11/29/2022 | 2022-07-12 | 80% | framework done, wait for debugging
2. Script language interpreter for APP generation | 2.1 | Script language interpreter | 2022-08-12 | 12/16/2022 | 80%
| 2.2 | Script lanugage command (interface) | 12/17/2022 | 12/27/2022 | 50% | OO, PO, For, Inherit
3. Python API corpus collection | 3.1 | API specification extraction by static analysis | 12/28/2022 | 2023-08-01 | 80% | Exception collection
| 3.2 | Dynamic type extraction for API specifications | 2023-09-01 | 01/31/2023 | 50% | In debugging and testing
| 3.3 | API dependence extraction | 2023-01-01 | 02/15/2023 | 0% | Jiawei is working on it
4. Experiment | 4.1 | No baseline, Consistent fuzzing on cpython | 2023-01-03 | 03/31/2023 | 0% | need test design
5. Paper writting | 5.1 | Motivation | 2023-01-04 | 2023-05-04 | 0%
| 5.2 | Methology | 2023-06-04 | 2023-10-04 | 0%
| 5.3 | Results | 2023-11-04 | 04/13/2023 | 0%
| 5.4 | Related work | 04/14/2023 | 04/15/2023 | 0%
| 5.5 | Introduction | 04/16/2023 | 04/20/2023 | 0%
| 5.6 | Abstract & conclusion | 04/21/2023 | 04/21/2023 | 0%
Motivation | 1. Python language has been widely applied in variouse domains, hence as the foundation, the quality of python interpreter and runtime is essential. 2. There hunderds of bugs/vulnerabilities in cpython triggerred by developers => show the data (overall, statistics by year). 3. None existing techniques can automatically test cpython, limited test cases can not guarantee the quality either. 4. We need a automatic and consistent technique for python (interpreter + runtimes) testing before the bugs/vulnerabilities sinked to applications, hence cpython fuzzing is a choice
Challenges | 1. consistent fuzzing on both interpreter core and runtimes 2. deverse and runable python application generation for runtime apis
Contributions | as challenges
Technology | 1. two-level fuzzing framework: fuzzing interpreter core and rumtimes at same time through shared coverage feedback but different fuzzing instances 2. through summarizing the basic structure or semantics of python applicaton, develop a interpreted-language based APP generation
Experiments | In addition to the bug report, some metrics are necessary for demonstration in the paper. (need a system test design)